## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during development and include a detailed description of every step. Explain what problems you encountered, why you made certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log. If external sources where used as reference, please mention them in the description
Subject | Amount of hours | Date | Description | Bonus
Getting to know the project | 2 | 2023-05-16 | Reading all the information a few times, downloading and installing software and setting up project. I had some problems with installing the composer and routing.
Research and preparation | 2 | 2023-05-17 | Looking through the repository, routing and trying to understand how it all works. Since I didn't develop REST API in PHP before I was a bit confused, watched a short tutorial on youtube (https://www.youtube.com/watch?v=pqEONSbXeSQ) and then started to play around.
Setting up database and start working | 1 | 2023-05-17 | Createad and populated the database, start working on /getall and /getone endpoints. At first I created a repository class (I am used to MVC) in where I was having the queries, but because of a db problem I moved it all in controller.
Working on assignment | 1 | 2023-05-18 | Created all endpoints on a basic level and tested them. I created a new method that is pretty much same as executeQuery but it returns an array instead of boolean. For testing purposes
Working on requirements | 2 | 2023-05-19 | Going over the requirements and improving endpoints according to REST style. Made a new method to get the request data based on content type and sanitize it. Implemented pagination.
User story 3 + fix user story 1 | 1 | 2023-05-20 | While working on user story 3, I realised that I missed something in the requirements regarding the database (a Facility can have multiple Tags), so I had to change the database and all the previous queries. After that implemented the search endpoint successfully. Here I understood that I need extra methods for creating and updating a new tag/location (so when creating a new facility, you can create a new location or tag instead of choosing from existing ones),
Manage Locations | 1 | 2023-05-20 | Created a method to manage locations and added it inside createOne and updateOne method, so when a new facility is created or updated - a new location will be inserted in database if it's not there already.
Manage Tags | 3 | 2023-05-20 | Here I had some problems with the tags. Since I added a new table in database (facility_tags) everything changed and got a bit more complicated. Then I took it step by step and made a lot of methods for it. In the end I still have a problem when inserting a new facility with tags, but i managed to fix the update method completly.
API documentation | 2 | 2023-05-20 | I haven't worked with Postman untill now, even while checking I was using Insomnia. So, I had to do some research on it and on API documentation. https://learning.postman.com/docs/publishing-your-api/documenting-your-api/ and checked some examples of API inside Postman. Then using I imported the colection that was in repository and started to build on it.
Review | 1 | 2023-05-21 | Reviewing the code and adding comments to it. While testing I had a problem with the XAMPP and when trying to fix I deleted some data, but luckily I had a copy of database and imported it again.
Finishing up | 1 | 2023-05-21 | Checking everything again, here I found some problems that could be improved, but I don't have more time right now. It was a new experience working with API in PHP and I'd like to learn more about it.
Applying feedback | 1 | 2023-06-08 | Fixed search endpoint to apply none,1 or more filters. Returning the facility when creating and updating it.Removed some unnecessary comments, fixed pagination, added sanitization to all other endpoints, added model classes.
Applying feedback | 1 | 2023-06-09 | Fixing Postman Collection
Total amount of hours | 19